## Estimate
Wall of Honor					$100.00

Item	Feature	Category	Low	Norm	High	PERT	Cost

Hosting Setup	General	Infrastructure	1	2	3	2	$200.00
CI/CD Setup	General	Infrastructure	1	2	4	2.2	$220.00
Framework	General	Infrastructure	1	2	4	2.2	$220.00
Data Migration	General	Infrastructure	3	4	8	4.5	$450.00
Documentation	General	Infrastructure	2	4	8	4.3	$430.00
General Communication/Overhead	General	Communication	2	4	8	4.3	$430.00
Design Language/Inspiration	General	Design	2	4	6	4	$400.00

Requirements Gathering	Deceased Ministers	Communication	0.5	2	4	2.1	$210.00
Administrative Interface (edit/update)	Deceased Ministers	Design	0.25	0.5	1	0.5	$50.00
Administrative Interface (edit/update)	Deceased Ministers	Implementation	0.5	2	6	2.4	$240.00
Overview Page	Deceased Ministers	Design	0.5	1	3	1.3	$130.00
Overview Page	Deceased Ministers	Implementation	0.25	1	2	1	$100.00
View #1 (By Year?)	Deceased Ministers	Design	0.25	0.5	1	0.5	$50.00
View #1 (By Year?)	Deceased Ministers	Implementation	0.25	0.5	1	0.5	$50.00
View #2 (Alphabetic?)	Deceased Ministers	Design	0.25	0.5	1	0.5	$50.00
View #2 (Alphabetic?)	Deceased Ministers	Implementation	0.25	0.5	1	0.5	$50.00
Minister Detail View	Deceased Ministers	Design	0.25	0.5	1	0.5	$50.00
Minister Detail View	Deceased Ministers	Implementation	0.25	1	2	1	$100.00
Feedback, Redesign, and Rework	Deceased Ministers	Design	0.5	1	2	1.1	$110.00
Feedback, Redesign, and Rework	Deceased Ministers	Implementation	0.5	1	2	1.1	$110.00

Requirements Gathering	Executive Leadership	Communication	0.5	2	4	2.1	$210.00
Administrative Interface (edit/update)	Executive Leadership	Design	0.25	0.5	1	0.5	$50.00
Administrative Interface (edit/update)	Executive Leadership	Implementation	0.5	4	8	4.1	$410.00
Overview Page	Executive Leadership	Design	0.5	1	3	1.3	$130.00
Overview Page	Executive Leadership	Implementation	0.25	1	2	1	$100.00
Department View	Executive Leadership	Design	0.5	1	3	1.3	$130.00
Department View	Executive Leadership	Implementation	0.5	1	3	1.3	$130.00
Minister Detail View	Executive Leadership	Design	0.25	0.5	1	0.5	$50.00
Minister Detail View	Executive Leadership	Implementation	0.25	1	2	1	$100.00
Feedback, Redesign, and Rework	Executive Leadership	Design	0.5	1	2	1.1	$110.00
Feedback, Redesign, and Rework	Executive Leadership	Implementation	0.5	1	2	1.1	$110.00

Requirements Gathering	Order of the Faith	Communication	0.5	2	4	2.1	$210.00
Administrative Interface (edit/update)	Order of the Faith	Design	0.25	0.5	1	0.5	$50.00
Administrative Interface (edit/update)	Order of the Faith	Implementation	0.5	2	6	2.4	$240.00
Overview Page	Order of the Faith	Design	0.5	1	3	1.3	$130.00
Overview Page	Order of the Faith	Implementation	0.25	1	2	1	$100.00
Year View	Order of the Faith	Design	0.5	1	2	1.1	$110.00
Year View	Order of the Faith	Implementation	0.25	1	2	1	$100.00
Minister Detail View	Order of the Faith	Design	0.25	0.5	1	0.5	$50.00
Minister Detail View	Order of the Faith	Implementation	0.25	1	2	1	$100.00
Feedback, Redesign, and Rework	Order of the Faith	Design	0.5	1	2	1.1	$110.00
Feedback, Redesign, and Rework	Order of the Faith	Implementation	0.5	1	2	1.1	$110.00

Grand Total			25.25	60	126	64.9	$6,490.00

## Cost by Feature & Category
Sum - Cost	Category					Distributing General Across Features
Feature	Communication	Design	Implementation	Infrastructure	(empty)	Total Result		Deceased Ministers	$2,083.33
Deceased Ministers	$210.00	$440.00	$650.00			$1,300.00		Executive Leadership	$2,313.33
Executive Leadership	$210.00	$470.00	$850.00			$1,530.00		Order of the Faith	$2,093.33
General	$430.00	$400.00		$1,520.00		$2,350.00
Order of the Faith	$210.00	$450.00	$650.00			$1,310.00
(empty)
Total Result	$1,060.00	$1,760.00	$2,150.00	$1,520.00		$6,490.00

Cost Adjusted	85.67%
Sum - Cost	Category
Feature	Communication	Design	Implementation	Infrastructure	(empty)	Total Result
Deceased Ministers	$179.91	$376.95	$556.85			$1,113.71
Executive Leadership	$179.91	$402.65	$728.19			$1,310.75
General	$368.38	$342.68		$1,302.18		$2,013.24
Order of the Faith	$179.91	$385.51	$556.85			$1,122.27
(empty)
Total Result	$908.10	$1,507.79	$1,841.90	$1,302.18		$5,559.97

## Time by Feature & Category
Sum - PERT	Data
Feature	Communication	Design	Implementation	Infrastructure	(empty)	Total Result
Deceased Ministers	2.1	4.4	6.5			13
Executive Leadership	2.1	4.7	8.5			15.3
General	4.3	4		15.2		23.5
Order of the Faith	2.1	4.5	6.5			13.1
(empty)
Total Result	10.6	17.6	21.5	15.2		64.9
						6.49

## Cost (for SOW)
General
Infrastructure Design and Implementation	$640.00
Design Research & Groundwork	$400.00
Documentation & Communication	$860.00
Data Migration/Import	$450.00
Total	$2,350.00

Executive Leadership Display
Requirements and Design Feedback	$430.00
Administrative Interface (edit/update)	$460.00
Overview Page	$230.00
Department View	$260.00
Minister Detail View	$150.00
Total	$1,530.00

Order of the Faith
Requirements and Design Feedback	$430.00
Administrative Interface (edit/update)	$290.00
Overview Page	$230.00
Year View	$210.00
Minister Detail View	$150.00
Total	$1,310.00

Deceased Ministers
Requirements and Design Feedback	$430.00
Administrative Interface (edit/update)	$290.00
Overview Page	$230.00
Organize by Year	$100.00
Organize by Name	$100.00
Minister Detail View	$150.00
Total	$1,300.00

Grand Total	$6,490.00